## Issues
issuekey | Summary | TestStep | Test Data | Test Result | Status Category Changed | Issue Type | Time Spent | Total forms | Project | Category | Fix versions | Σ Time Spent | Resolution | Work category | Approvals | Request participants | Locked forms | Open forms | Submitted forms | Resolved | Work Ratio | Last Viewed | Watchers | Created | Sprint | Flagged | Target start | Priority | Target end | [CHART] Date of First Response | [CHART] Time in Status | Labels | Compass | Story point estimate | Issue color | Parent Link | Rank | Remaining Estimate | Σ Original Estimate | Affects versions | Linked Issues | Assignee | Assignee-account-id | Updated | Status | Components | Original estimate | Description | Request Type | Epic Link | Start date | Change type | Change risk | Security Level | Change reason | Actual start | Σ Remaining Estimate | Actual end | Creator | Creator-account-id | Sub-tasks | Atlas project key | Atlas project status | Reporter | Σ Progress | Team | Organizations | Approvers | Impact | Satisfaction | Satisfaction date | Environment | Due date | Progress | Votes
PROJ-26 | firefox browser tester | we open firefox browser |  | browser is open | 2023-07-26T11:12:41.116+0200 | Test |  |  | ProjectOpenCart |  |  |  | Done | [6 empty] | 2023-07-26T11:12:41.112+0200 | -1 | 2023-08-11T19:57:24.973+0200 | 1 | 2023-07-26T11:06:50.052+0200 |  |  |  | Medium |  |  | 10000_*:*_1_*:*_351095_*¦*_10002_*:*_1_*:*_0 |  |  |  |  | The Parent Link is only available to Jira Premium users. | 0¦i000ev: |  |  |  | PROJ-23 |  |  | 2023-08-11T19:57:41.976+0200 | Done |  |  | we run a test for log in to site on firefox browser | [10 empty] | Lucian Bogdan Scutariu | 712020:c24c465f-8605-4b8b-b6b4-d7575e1ab534 |  |  |  | Lucian Bogdan Scutariu | 0 | [8 empty] | 0 | 0
|  | we acces the site | https://demo.opencart.com/ | page is loaded
|  | we click on my account |  | menu for my acount is open
|  | we click on login |  | login page is open
|  | we insert fals username an false password and click login |  | login failed
|  | we recive a message | username and passort wrong inserted | message recived
|  | we insert the corect user and password | log in button | home page is open
PROJ-25 | internet explorer test | we open internet explorer |  | browser is open | 2023-07-26T11:05:34.558+0200 | Test |  |  | ProjectOpenCart |  | Test Released |  | Done | [6 empty] | 2023-07-26T11:05:34.554+0200 | -1 | 2023-08-11T19:58:19.359+0200 | 1 | 2023-07-26T10:57:22.347+0200 |  |  |  | Medium |  |  | 10000_*:*_1_*:*_492238_*¦*_10002_*:*_1_*:*_0 |  |  |  |  | The Parent Link is only available to Jira Premium users. | 0¦i000en: |  |  |  | PROJ-23 |  |  | 2023-07-26T11:05:34.558+0200 | Done |  |  | we test the site with internet explorer and we try to log in in the account | [10 empty] | Lucian Bogdan Scutariu | 712020:c24c465f-8605-4b8b-b6b4-d7575e1ab534 |  |  |  | Lucian Bogdan Scutariu | 0 | [8 empty] | 0 | 0
|  | we open the link | https://demo.opencart.com/ | page is loaded
|  | we click on my account button |  | menu is open
|  | we click on log in |  | login page is open
|  | we insert false user name |  | field is complet
|  | we write corect password |  | user field is complet
|  | we click on log in |  | login failed
|  | we recive a messege | username not found | message recived
|  | we write corect user and corect passwort |  | login succesfuly
PROJ-24 | chrome test | we open google chrome browser | N/A | browser is open | 2023-07-26T11:05:31.756+0200 | Test |  |  | ProjectOpenCart |  | Test Released |  | Done | [6 empty] | 2023-07-26T11:05:31.753+0200 | -1 | 2023-08-11T19:58:35.175+0200 | 1 | 2023-07-26T10:44:35.078+0200 |  |  |  | Medium |  |  | 10000_*:*_1_*:*_1256703_*¦*_10002_*:*_1_*:*_0 |  |  |  |  | The Parent Link is only available to Jira Premium users. | 0¦i000ef: |  |  |  | PROJ-3 |  |  | 2023-07-26T11:05:31.756+0200 | Done |  |  | we will open the google chrome to test the site | [10 empty] | Lucian Bogdan Scutariu | 712020:c24c465f-8605-4b8b-b6b4-d7575e1ab534 |  |  |  | Lucian Bogdan Scutariu | 0 | [8 empty] | 0 | 0
|  | we insert the website in the adress field | https://demo.opencart.com/ | page is open
|  | we click on log in |  | menu log in is open
|  | we inser user name |  | user name field is completed
|  | we insert a wrong password |  | password is complet
|  | we click on the log in button |  | log in failed
|  | we recived a message | insert the corect password | message recived
|  | we click on passwort and we write the corect password |  | logged in succesfully main page is loaded
PROJ-17 | complet personal details and place order | we acces the main page | https://demo.opencart.com/index.php?route=common/home&language=en-gb | main page is accesed | 2023-07-26T10:30:56.628+0200 | Test |  |  | ProjectOpenCart |  | Test Released |  | Done | [6 empty] | 2023-07-26T10:30:56.625+0200 | -1 | 2023-08-11T20:06:00.331+0200 | 1 | 2023-07-25T13:52:22.563+0200 |  |  |  | Medium |  |  | 10000_*:*_1_*:*_74314093_*¦*_10002_*:*_1_*:*_0 |  |  |  |  | The Parent Link is only available to Jira Premium users. | 0¦i000cv: |  |  |  | PROJ-18,PROJ-19,PROJ-20,PROJ-21,PROJ-22,PROJ-16,PROJ-18,PROJ-19,PROJ-20,PROJ-21,PROJ-22 |  |  | 2023-07-26T10:30:56.628+0200 | Done |  |  | we will inser out personall details and shipping adress the we will place the order | [10 empty] | Lucian Bogdan Scutariu | 712020:c24c465f-8605-4b8b-b6b4-d7575e1ab534 |  |  |  | Lucian Bogdan Scutariu | 0 | [8 empty] | 0 | 0
|  | we click on check out button |  | page is opened
|  | we fill the firs name | Scutariu | name is inserted
|  | we fill last name | Lucian Bogdan | field complet
|  | we fill the adress | alfred 128 | adress is complet
|  | we write the city | erfurt | field complet
|  | we complet country field | Germany | done
|  | we write aswell the Region/State | Thuringe | complet
|  | we go down the page and we press continue | N/A | new page is diplay
|  | we choose the I want to use an existing address for payment adress and for shipping adress |  | done
|  | we chose the shipping method | DPD | Shipping box is complet
|  | we choose payment method | visa card | Payment accepted
|  | we write account details | N/A | card details inserted
|  | we make click on confirm order |  | order finish
|  | we need to recive on email details with our order nr |  | email is confirmed
PROJ-14 | we will add a voucher in the voucher field | we acces the website | https://demo.opencart.com/index.php?route=common/home&language=en-gb | page is open | 2023-07-25T13:45:20.357+0200 | Test |  |  | ProjectOpenCart |  | Test Released |  | Done | [6 empty] | 2023-07-25T13:45:20.353+0200 | -1 | 2023-08-11T20:10:35.055+0200 | 1 | 2023-07-25T13:25:01.039+0200 |  |  |  | Medium |  |  | 10000_*:*_1_*:*_1219342_*¦*_10002_*:*_1_*:*_0 |  |  |  |  | The Parent Link is only available to Jira Premium users. | 0¦i000c7: |  |  |  | PROJ-15,PROJ-13,PROJ-15 |  |  | 2023-07-25T13:45:20.357+0200 | Done |  |  | after we have some products in the cart we will see if we can use a voucher code | [10 empty] | Lucian Bogdan Scutariu | 712020:c24c465f-8605-4b8b-b6b4-d7575e1ab534 |  |  |  | Lucian Bogdan Scutariu | 0 | [8 empty] | 0 | 0
|  | we add one product in cart | Samsung SyncMaster 941BW | product are insert in cart
|  | we click on Shopping cart |  | cart is open
|  | we need to find field for voucher that supposed to be under the products |  | we find the field
|  | we go down to page we press the "USE COUPON CODE" | Reducere99 | field is complet
|  | we check the total price if the voucher is applyed |  | price is reduced
PROJ-10 | preview the image for the products and adding product in cart | we acces the main page | https://demo.opencart.com/index.php?route=common/home&language=en-gb | pagin is loaded | 2023-07-25T13:19:46.382+0200 | Test |  |  | ProjectOpenCart |  |  |  | Done | [6 empty] | 2023-07-25T13:19:46.379+0200 | -1 | 2023-08-11T20:21:30.149+0200 | 1 | 2023-07-25T12:59:06.305+0200 |  |  |  | Medium |  |  | 10000_*:*_1_*:*_1240102_*¦*_10002_*:*_1_*:*_0 |  |  |  |  | The Parent Link is only available to Jira Premium users. | 0¦i000bb: |  |  |  | PROJ-12,PROJ-6,PROJ-11,PROJ-12 |  |  | 2023-08-11T19:59:24.978+0200 | Done |  |  | we will chose one product and wi will inspect the information and photo that we have then we will added in to cart | [10 empty] | Lucian Bogdan Scutariu | 712020:c24c465f-8605-4b8b-b6b4-d7575e1ab534 |  |  |  | Lucian Bogdan Scutariu | 0 | [8 empty] | 0 | 0
|  | we click on Component menu and we click on show all component | N/A | page with component is open
|  | we click on monitors |  | page is open
|  | we chose one monitor | Apple Cinema 30" | pagine with the monitor is open
|  | we read the info we take a look for images and we insert it in to the cart |  | product is added to cart
PROJ-9 | adding more product in cart | we acces the main page | https://demo.opencart.com/index.php?route=common/home&language=en-gb | main page is loaded | 2023-07-25T12:55:36.829+0200 | Test |  |  | ProjectOpenCart |  | Test Released |  | Done | [6 empty] | 2023-07-25T12:55:36.826+0200 | -1 | 2023-08-11T19:59:17.225+0200 | 1 | 2023-07-25T12:40:29.627+0200 |  |  |  | Medium |  |  | 10000_*:*_1_*:*_907231_*¦*_10002_*:*_1_*:*_0 |  |  |  |  | The Parent Link is only available to Jira Premium users. | 0¦i000b3: |  |  |  | PROJ-6 |  |  | 2023-07-25T12:55:36.829+0200 | Done |  |  | we will find more products and we will add all in the cart then we will acces the cart | [10 empty] | Lucian Bogdan Scutariu | 712020:c24c465f-8605-4b8b-b6b4-d7575e1ab534 |  |  |  | Lucian Bogdan Scutariu | 0 | [8 empty] | 0 | 0
|  | we acces the laptop and notebook menu |  | page is open
|  | we chose one laptop and we read the info then we addd in the cart | HP LP3065 | product is added succesfuly in cart
|  | we chose another paroduct and we added to cart | Samsung SyncMaster 941BW | product is sended to cart
|  | we go on tablets menu |  | tablets page in open
|  | we chose one tablet and we insert in cart | Samsung Galaxy Tab 10.1 | product is in cart
|  | we go on the cart to see if we have all product in cart | press cart logo | cart windows in open all products are in cart
PROJ-7 | Checking the Desktops menu | we open main page | https://demo.opencart.com/index.php?route=common/home&language=en-gb | page is loaded | 2023-07-24T13:06:09.150+0200 | Test |  |  | ProjectOpenCart |  | Test Released |  | Done | [6 empty] | 2023-07-24T13:06:09.146+0200 | -1 | 2023-08-11T19:59:11.043+0200 | 1 | 2023-07-24T12:55:38.070+0200 |  |  |  | Medium |  |  | 10000_*:*_1_*:*_631109_*¦*_10002_*:*_1_*:*_0 |  |  |  |  | The Parent Link is only available to Jira Premium users. | 0¦i000av: |  |  |  | PROJ-6 |  |  | 2023-07-24T13:12:27.713+0200 | Done |  |  | we will controll the destop menu to see what tipe of desktop`s we can buy and inserted in cart | [10 empty] | Lucian Bogdan Scutariu | 712020:c24c465f-8605-4b8b-b6b4-d7575e1ab534 |  |  |  | Lucian Bogdan Scutariu | 0 | [8 empty] | 0 | 0
|  | we search desktops menu and we click on it | N/A | main Page is loaded
|  | we click on a computer that we like | iMac | page is open
|  | we insert in to cart |  | the item is inserted and the cart loaded
|  | we click on logo Opencart to go on main page | N/A | Main pagen is loaded
|  | we click on cart button to see if we have the pc added |  | cart page is loaded succesfuly
PROJ-4 | we will check the payments methods | we make click on my account button | N/A | My account menu is open | 2023-07-24T12:48:37.468+0200 | Test |  |  | ProjectOpenCart |  | Test Released |  | Done | [6 empty] | 2023-07-24T12:48:37.464+0200 | -1 | 2023-08-11T19:59:33.119+0200 | 1 | 2023-07-24T12:14:44.260+0200 |  |  |  | Medium |  |  | 10000_*:*_1_*:*_2033234_*¦*_10002_*:*_1_*:*_0 |  |  |  |  | The Parent Link is only available to Jira Premium users. | 0¦i000a7: |  |  |  | PROJ-5,PROJ-2,PROJ-5 |  |  | 2023-07-24T12:48:37.467+0200 | Done |  |  | we will check what tips of payment methods we have and we will insert our details | [10 empty] | Lucian Bogdan Scutariu | 712020:c24c465f-8605-4b8b-b6b4-d7575e1ab534 |  |  |  | Lucian Bogdan Scutariu | 0 | [8 empty] | 0 | 0
|  | we prress the payment method button | N/A | a new page with payments method is open
|  | we check what tips of payment we have and we insert our bank details | Name Last Name tip of card expiring date CVV | Payment details are succesfuly inserted
PROJ-3 | Acces the wesite and create a new user | we open the browser | google.com | browser is open | 2023-07-24T12:13:00.409+0200 | Test |  |  | ProjectOpenCart |  |  |  | Done | [6 empty] | 2023-07-24T12:13:00.405+0200 | -1 | 2023-08-16T10:45:35.975+0200 | 1 | 2023-07-24T11:44:01.312+0200 |  |  |  | Medium |  |  | 10000_*:*_1_*:*_1739123_*¦*_10002_*:*_1_*:*_0 |  |  |  |  | The Parent Link is only available to Jira Premium users. | 0¦i0009z: |  |  |  | PROJ-24,PROJ-2 |  |  | 2023-08-11T19:59:53.284+0200 | Done |  |  | In this step we will acces the platform and we will create a new user with all personal details | [10 empty] | Lucian Bogdan Scutariu | 712020:c24c465f-8605-4b8b-b6b4-d7575e1ab534 |  |  |  | Lucian Bogdan Scutariu | 0 | [8 empty] | 0 | 0
|  | we click on the field to write the website | https://demo.opencart.com/ | Main Page is opened
|  | we click on my account button | N/A | My account menu is open
|  | we click on register | N/A | the page for registration is open
|  | we make click on the first name Field and we write the first name. | Scutariu | name is inserted
|  | we make click on the lastt name Field and we write the last name. | Bogdan-Lucian | last name ist insterted
|  | we write the email adress in the Email box | scutariu.lucian89@yahoo.com | email is insterted in the field
|  | we insert a passwort |  | passwort is inserted
|  | we make click on "I have read and agree to the Privacy Policy" box and after click on continue |  | we created succesfully a new account